## Test Plan
Please click here for Bdstall web application testplan full PDF.

## Mind Maps
Mind Map of Bdstall Web Application

## TestScenarios
Project Name | Bdstall
Reference Document | FRS
Created By | Progga Roy
Creation Date | 2025-03-10
Approval Date
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 | User Management | Validate user "Registration" with email and password | P0
TS_002 | User Management | Verify Facebook authentication for "Login" | P0
TS_003 | User Management | Validate the "Logout" functionality | P0
TS_004 | User Management | Validate the working of "Forgotten Password?" functionality. | P0
TS_005 | User Management | Validate the "Profile updates" | P1
TS_006 | User Management | Validate the "control panel access" | P1
TS_007 | User Management | Validate the functionality of uploading file | P1
TS_008 | UI & Navigation | Validate the header elements like "logo, points button,etc." | P2
TS_009 | UI & Navigation | Validate the "Search" functionality | P3
TS_0010 | UI & Navigation | Validate the "Banner" functionaity | P3
TS_0011 | UI & Navigation | Validate responsive design across different screen sizes | P0
TS_0012 | UI & Navigation | Checks blog,FQA, and social meadia links | P4
TS_0013 | UI & Navigation | Validate website compatibility across multiple browsers. | P0
TS_0014 | Product Management | Verify user can add and remove product from cart | P0
TS_0015 | Product Management | Verify price calculation from the cart | P0
TS_0016 | Product Management | Validate category-based filtering functionality | P3
TS_0017 | Product Management | Check price range filtering and location-based filtering | P3
TS_0018 | Product Management | Validate pagiination handling | P3
TS_0019 | Product Management | Validate review and rating functionality | P3
TS_0020 | Seller Management | Validate online stall creation process | P1
TS_0020 | Communication System | Validate "Call now " button functionality | P1
TS_0021 | Communication System | Validate "Contact Us " functionality | P2
TS_0022
TS_0023 | Order and payment | Validate order placement and confirmation | P0
TS_0024 | Order and payment | Validate payment method | P0
TS_0025 | Order and payment | Validate payment successful massege | P0

## TestCase
Product Name |  | BdStall | TC Start Date | 2025-03-10 | TC Execution Start Date | - - | [5 empty] | TEST CASE
Module Name |  | Account | TC End Date | 2025-03-13 | TC Execution End Date | - - |  |  |  |  | PASS | 79
Epic |  |  | Test Case Developed By | Progga Roy | Browser (tested) | Yes |  |  |  |  | FAIL | 5
Developer Name (TL) |  |  | Test Case Reviewed By | Ehsanul Alam Sabbir | Performance (tested) | No |  |  |  |  | NO RUN | 0
Test Executed by | [10 empty] | BLOCKED | 0
[11 empty] | TOTAL | 84
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
1 | Account | Browser Compatibility Testing | Account | Checkinging by running the URL site in different browsers. | Should be run in different browsers. | As expected | Browsers-Chrome, Internet Explorer, Mozilla Firefox, Microsoft Edge, Opera Mini.Browsers-Chrome, Internet Explorer, Mozilla Firefox, Microsoft Edge, Opera Mini. | 1. Go to different browsers. 2. Search 'Startech' 3. Go to the website. |  |  | Passed
2 | User Authentication |  | Login | Verifying that the login page loads correctly | Login page should loads without any errors,displaying all elements properly | As expected | None | 1.Open Browser https://www.bdstall.com/ 2. Navigate the login page |  |  | Passed
2 |  |  |  | Verifying all login-related elements and fields are present on the login page. | Should be present the all mandatory field | As expected | None | 1. Goto the URL http://localhost:1337 2. Click on the "Login" button in the right corner. |  |  | Passed
3 |  |  |  | Verifying password is masked | Password should be displayed dots or asterisks (*) | As expected | None | 1. Open browser https://www.bdstall.com/ 2. Click on the "Login" button in the right corner.3.Enter password |  |  | Passed
4 |  |  |  | Verifying password visibility using the eye icon | Password field should have an eye icon to allow users to toggle visibility | Not as expected | None | 1. Open Browser https://www.bdstall.com/ 2. Click on the "Login" button in the right corner. 3. Locate the password field 4. Observe that the eye icon is missing | Missing-eye-icon |  | Failed
5 |  |  |  | Verifyinglogin fails with incorrect credentials | An error message should appear: "Invalid username or password." | As expected | None | 1. Open Browser https://www.bdstall.com/ 2. Enter wrong credentials. 3. Click Login. |  |  | Passed
6 |  |  |  | Verifying error message when password is empty | A pop up message should appear: "Please provide password" | As expected | None | 1. Open Browser https://www.bdstall.com/ 2. Enter email. 3. Leave password blank. 4. Click Login. |  |  | Passed
3 |  |  |  | Verifying error message when email is empty | A pop up message should appear: "Please provide email" | As expected | None | 1. Open Browser https://www.bdstall.com/ 2. Leave email field 3. Leave password blank. 4. Click Login. |  |  | Passed
|  |  |  | Verifying login with invalid email format | An error message should appear: "Enter a valid email address." | As expected | None | 1. Open Browser https://www.bdstall.com/ 2. Enter invalid email. 3. Click Login. |  |  | Passed
4 |  |  |  | Verifying Login with valid credentials presseing "Enter" key or clicking "login button" | User should be logged in successfully and redirected to the homepage/dashboard. | Not As expected | None | 1. Open Browser https://www.bdstall.com/ 2. Click on the "Login" button in the right corner. 3. Enter correct credentials 4.Click on "login" button | Failed Manual login.png |  | Failed
5 |  |  |  | Verifying successful "Google Signin" | User should be logged in successfully. | As expected | None | 1. Open Browser https://www.bdstall.com/ 2. Click on the " sign in with google" 3. Select account. |  |  | Passed
|  |  |  | Verifying Google Sign-In button or link is available on the login page | "Sign in with Google" button should be displayed correctly and clickable. | As expected | None | 1. Open Browser https://www.bdstall.com/ 2.Open the login page. 3. Check if the "Sign in with Google" button is visible and properly aligned. |  |  | Passed
|  |  |  | Verifying Google Sign-In button is clickable and responsive | Google authentication page should open in a new tab/pop-up. | As expected | None | 1. Open Browser https://www.bdstall.com/ 2.Open the login page. 3. Click on the "Sign in with Google" button. |  |  | Passed
|  |  |  | Verifying Google Sign-In confirmation | User should login on the home page. | As expected |  | 1. Open Browser https://www.bdstall.com/ 2.Open the login page. 3. Click "Sign in with Google". 2. Close the pop-up with selecting an account. |  |  | Passed
14 |  |  |  | Verifying the displayed error message grammar should be correct. | The error message should be grammatically correct. | As expected | None | 1. Open Browser https://www.bdstall.com/ 2.Open the login page. 3. Enter invalid credentials 4.Click on "login" button |  |  | Passed
15 |  |  |  | Verifying the displayed error message spell should be correct. | The spelling of error message should be correct. | As expected | None | 1. Open Browser https://www.bdstall.com/ 2.Open the login page. 3. Enter invalid credentials 4.Click on "login" button |  |  | Passed
19 |  |  |  | Verifying the login screen will appear after clicking on a login link or login button. | The login screen should appear after clicking the login link or button. | As expected | None | 1. Open Browser https://www.bdstall.com/ 2.Open the login page. |  |  | Passed
20 |  |  |  | Verifying that the login page of the application is responsive and aligns properly on different screen resolutions and devices. | The login page should be responsive and properly aligned on different screen resolutions and devices. | As expected | None | 1. Goto the URL http://localhost:1337 2. Click on the "Login" button in the right corner. 3. Enter valid credentials 4.Click on "login" button 5. Right click on the mouse 6. Click on Inspect 7. Click toggle device toolbar 8. Checking with different device dimensions |  |  | Passed
21 |  |  |  | Verifying login page title. | The login page should display the correct title as per the application’s specifications. | As expected | None | 1. Goto the URL http://localhost:1337 2. Click on the "Login" button in the right corner. |  |  | Passed
22 |  |  |  | Verifying if keyboard shortcut keys enable in the text area. Users can copy, cut or paste and select content on shift + Arrow Keys. | Keyboard shortcuts (copy, cut, paste, Shift + Arrow) should work in the text area. | As expected | None | 1. Go to the URL http://localhost:1337 2. Click on the Login button in the right corner. 3. Paste/Copy/Cut an registered email 4. Click on Submit button |  |  | Passed
23 |  |  |  | Verifying that the text area is functional in case of any validation error message shown. | The text area should be functional during validation errors. | As expected | None | 1. Go to the URL http://localhost:1337 2. Click on the Login button in the right corner. 3. Enter invalid email 4. Enter Password 5. Click on Submit button 6. Enter another email |  |  | Passed
24 |  |  |  | Verifying Backspace, delete keys should be functional | Backspace and Delete keys should be functional in the text area. | As expected | None | 1. Go to the URL http://localhost:1337 2. Click on the Login button in the right corner. 3. Enter a registered email 4.Enter Backspace/Delete key |  |  | Passed
25 |  |  |  | Verifying user can paste the copied content with keyboard keys Ctrl + v. | User should be able to paste copied content using Ctrl + V. | As expected | None | 1. Go to the URL http://localhost:1337 2. Click on the Login button in the right corner. 3. Press Ctrl+V at the email text field 4. Enter password 5. Click on Submit button |  |  | Passed
27 |  |  |  | Verifying user can type in the text area after clicking in the text area. | User should be able to type in the text area after clicking on it. | As expected | None | 1. Go to the URL http://localhost:1337 2. Click on the Login button in the right corner. 3. Enter text in the textfield of email/passowrd |  |  | Passed
28 |  |  |  | After the user login page is open, the curson should remain in the username text box by default. | After the login page is opened, the cursor should remain in the username text box by default. | Not found as per expectation. | None | 1. Goto the URL http://localhost:1337 2. Click on the "Login" button in the right corner. | Cursor_Error |  | Failed
29 | User Registration |  | Registration | Verify "Not registered yet? Click here" link is avabilbe in the login page | The registration link should be displayed and visible. | As expected. | None | 1.Open Browser https://www.bdstall.com/ 2.Open the login page. 1. Click on the "Not registered yet? Click here" link. |  |  | Passed
30 |  |  |  | Verify clicking on the "Not registered yet? Click here" link redirects the user to the registration page | The user should be redirected to the registration page. | As expected. | None | 1.Open Browser https://www.bdstall.com/ 2.Open the login page. 1. Click on the "Not registered yet? Click here" link. |  |  | Passed
31 |  |  |  | Verify that the registration link is properly aligned and clickable | The registration link should be aligned correctly and clickable. | As expected. | None | 1.Open Browser https://www.bdstall.com/ 2.Open the login page. 3. Inspect the registration link visually. 3. Click on it |  |  | Passed
|  |  |  | Verifying all fields related to registration present on the registration form. | The registration form should be displayed with all required fields. | As expected. | None | 1.Open Browser https://www.bdstall.com/ 2. Open the registration page. 3 Check for the presence of fields . |  |  | Passed
|  |  |  | Verify that the system unique security code. | A unique security code should be visible | As expected. | None | 1.Open Browser https://www.bdstall.com/ 2. Open the registration page. 3 Check for the security number. |  |  | Passed
|  |  |  | Verify that the system unique security code data-type | Unique security code should be number | As expected. | None | 1.Open Browser https://www.bdstall.com/ 2. Open the registration page. 3 Check for the security number. |  |  | Passed
|  |  |  | Verify that the user cannot proceed without entering the security code | A pop up message should appear: "Please provide security code" | As expected. | None | 1.Open Browser https://www.bdstall.com/ 2. Open the registration page. 3 Check for the security number. |  |  | Passed
|  |  |  | Verify that the system does not accept an expired security code | Provide new security code every ragistration | As expected. | None | 1. Open Browser https://www.bdstall.com/ 2. Click register link. 3.New security code |  |  | Passed
|  |  |  | Verifying that validation is added to the email field, only valid emails should be allowed to register successfully. | The email field should validate that only valid emails can be registered. | As expected. | None | 1. Open Browser https://www.bdstall.com/ 2. Click register link. 3. Enter valid email 5. Name 6.Security code 7. Click send code |  |  | Passed
|  |  |  | Verifying that the user adds blank spaces and clicks on the register button an error message should be shown. | An error message should be shown. | As expected. | None | 1. Open Browser https://www.bdstall.com/ 2. Click register link. 3. Blank 5. Name 6.Security code 7. Click send code |  |  | Passed
|  |  |  | Verifying users can register successfully by entering valid credentials. | Users should be able to send code successfully with valid credentials. | As expected. | None | 1. Open Browser https://www.bdstall.com/ 2. Click register link. 3. Enter valid email 5. Name 6.Security code 7. Click send code |  |  | Passed
|  |  |  | Verifying the varification code in the sending gmail address | Should be found the verification code in the gmail. | As expected. | None | 1. Open gmail.com 2. Enter valid email address 3.Found the code |  |  | Passed
|  |  |  | Verifying After registered "Login " link is available | Login link sholud be available after ragistration | As expected. | None | 1. Open Browser https://www.bdstall.com/ 2. After registration 3.Login link is available
|  |  |  | Verifying the massege "not found code in the inbox" | Should be found the verification code in the gmail spam | As expected. | None | 1. Open gmail.com 2. Enter valid email address 3.Found the code in the spam |  |  | Passed
|  |  |  | Verifying users can verify successfully by valid send code email address. | Users should be able to verify successfully with valid email. | As expected. | None | 1. Open Browser https://www.bdstall.com/ 2. Click register link. 3. Enter valid email 5. Name 6.Security code 7. Click send code. 8.Open gmail.com 9. Enter valid email address . |  |  | Passed
|  |  |  | Verifying users can verify successfully by verification code | Users should be able to verify successfully with verification code | As expected. | None | 1. Open Browser https://www.bdstall.com/ 2. Click register link. 3. Enter valid email 5. Name 6.Security code 7. Click send code. 8.Open gmail.com 9. Valid email address .10. enter verification code |  |  | Passed
|  |  |  | Verifying that the user adds blank spaces and clicks on the verify button a pop up should be shown. | A pop up should be shown. | As expected. | None | 1. Open Browser https://www.bdstall.com/ 2. Click register link. 3. Enter valid email 5. Name 6.Security code 7. Click send code. 8.Open gmail.com 9. Valid email address . 10.Blank 11. Error massage shown |  |  | Passed
|  |  |  | Verifying with the valid email and verification code | should be successfully registered | As expected. | None | 1. Open Browser https://www.bdstall.com/ 2. Click register link. 3. Enter valid email 5. Name 6.Security code 7. Click send code. 8.Open gmail.com 9. Valid email address . 10.Verification code.11.click verify code |  |  | Passed
|  |  |  | Verify that a user can copy the verification code from Gmail and paste it into the security code field. | The system should accept the correct security code and allow the user to proceed with registration. | As expected. | None | 1.Open gmail.com 2. Open Gmail and find the email. 3. Copy the verification code. 3. Open Browser https://www.bdstall.com/ 4.Click in register page 5. Paste it into the security code field. |  |  | Passed
|  |  |  | Verifying that the " verify button" is clickable ,aligned. | Button should be clickable | As expected. | None | 1. Open Browser https://www.bdstall.com/ 2. Click register link. 3. Enter valid email 5. Name 6.Security code 7. Click send code. 8.Open gmail.com 9. Valid email address . 10.Verification code.11.click verify code |  |  | Passed
|  |  |  | Verifying users can register successfully | Registerd successfully and redirections in the homepage/dashboard | As expected. | None | 1. Open Browser https://www.bdstall.com/ 2 Valid email address .2.Verification code.3.click verify code 4. Redirections to the homepage/dashboard |  |  | Passed
|  |  |  | Verifying successful massege"Verification code is your new password" in the registration page | After ragistration a successful massege should be there | As expected. | None | 1. Open Browser https://www.bdstall.com/ 2. Redirections to the homepage/dashboard 3. A confirming massage should be there |  |  | Passed
|  |  |  | Verifying all spelling mistakes on the Register page. | Spelling should be correct. | As expected. | None | 1. Open Browser https://www.bdstall.com/ 2. Redirections to the homepage/dashboard 3. Check spelling |  |  | Passed
32 | Search Functionality |  | Search | Verify that the search bar is present on the BD Stall website. | The search bar should be visible on the homepage. | As expected. | None | 1. 1. Open Browser https://www.bdstall.com/ 2. Check if the search bar is visible on the homepage. |  |  | Passed
33 |  |  |  | Verify that the search bar allows text input. | The user should be able to enter text into the search bar. | As expected. | None | 1. Open Browser https://www.bdstall.com/ 2. Click on the search bar. 3. Type a product name (e.g., "Laptop") |  |  | Passed
34 |  |  |  | Verify searching with a valid product name. | Relevant search results for "Laptop" should be displayed. | As expected. | None | 1. Open Browser https://www.bdstall.com/ 2. Type "Laptop" in the search bar. 3. Click on the search button or press Enter. |  |  | Passed
35 |  |  |  | Verify searching with an invalid product name. | A message like "No results found" should be displayed. | Not as expected. | None | 1. Open Browser https://www.bdstall.com/ 2. Type "@#*&^%$" in the search bar. 3. Click on the search button or press Enter.. | Not_found_massege_error.png |  | Failed
36 |  |  |  | Verify search with spaces before and after the keyword. | The spaces should be trimmed, and correct search results should be displayed. | As expected | None | 1. Open Browser https://www.bdstall.com/ 2. Type " Laptop " (with spaces). 3. Click the search button.. |  |  | Passed
37 |  |  |  | Verify auto-suggestion feature for incomplete words. | It should show suggestions like "Mobile, Mobile Case". | Not as expected. | None | 1. Open Browser https://www.bdstall.com/ 2. Type "Laptop" in the search bar. 3. Click on the search button or press Enter. | Search result not relevant with text |  | Failed
38 |  |  |  | Verify search results for a category name. | The results should display products under the Electronics category. | As expected | None | 1. Open Browser https://www.bdstall.com/ 2. Type "Electronics" in the search bar. |  |  | Passed
39 |  |  |  | Verify search results load within an acceptable time. | The results should load within 2-3 seconds. | As expected | None | 1. Open Browser https://www.bdstall.com/ 2. Perform a search. 3. Measure the time taken for results to appear.. |  |  | Passed
47 | Transaction Processing |  | Transaction Functionality | Verifying successful transaction with valid payment details | Transaction should be processed successfully with a confirmation message | Found as per expectation | None | 1. Open Browser https://www.bdstall.com/ 2. Measure the time taken for results to appear. 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Transactions 7. Click on Create New 8. Fill required fields with valid inputs 9. Click on Create |  |  | Passed
48 |  |  |  | Verifying transaction failure with invalid payment details. | Transaction should fail, and an error message should be displayed. | Found as per expectation | -10 | 1. Open Browser https://www.bdstall.com/ 2. Measure the time taken for results to appear. 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Transactions 7. Click on Create New 8. Fill required fields with valid inputs 9. Click on Create |  |  | Passed
49 |  |  |  | Verifying transaction with insufficient funds. | Transaction should be declined due to insufficient funds, with an appropriate error message | Found as per expectation | input>amount | 1. Open Browser https://www.bdstall.com/ 2. Measure the time taken for results to appear. 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Transactions 7. Click on Create New 8. Fill required fields with valid inputs 9. Click on Create |  |  | Passed
50 |  |  |  | Verifying transaction details are recorded correctly in the transaction history | Transaction details (amount, date, payment method) should appear accurately in the user's transaction history. | Found as per expectation | None | 1. Open Browser https://www.bdstall.com/ 2. Measure the time taken for results to appear. 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Transactions 7. Click on Create New 8. Fill required fields with valid inputs 9. Click on Create |  |  | Passed
51 |  |  |  | Verifying correct transaction amount is charged. | The charged amount should match the transaction amount. | Found as per expectation | None | 1. Open Browser https://www.bdstall.com/ 2. Measure the time taken for results to appear. 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Transactions 7. Click on Create New 8. Fill required fields with valid inputs 9. Click on Create |  |  | Passed
52 |  |  |  | Verifying user is notified upon successful transaction completion. | User should receive a notification (email/SMS) upon successful transaction. | Not found as per expectation | None | 1. Open Browser https://www.bdstall.com/ 2. Measure the time taken for results to appear. 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Transactions 7. Click on Create New 8. Fill required fields with valid inputs 9. Click on Create |  |  | Passed
53 | Inquiry Handling |  | Contact Us Functionality | Verifying user can initiate a "Contact Us" request via Facebook | Should able to send a direct message | Found as per expectation | None | 1. Open Browser https://www.bdstall.com/ 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Contact us 7. Goto the URL https://ssrd.io 8. Click on Contact us. 9. Click on twitter icon with a logged account |  |  | Passed
54 |  |  |  | Verifying user can initiate a "Contact Us" request via Twitter. | Should able to send a direct message | Found as per expectation | None | 1. Open Browser https://www.bdstall.com/ 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Contact us 7. Goto the URL https://ssrd.io 8. Click on Contact us. 9. Click on twitter icon with a logged account |  |  | Passed
55 |  |  |  | Verifying user can initiate a "Contact Us" request via LinkedI | Should able to send a direct message | Found as per expectation | None | 1. Open Browser https://www.bdstall.com/ 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Contact us 7. Goto the URL https://ssrd.io 8. Click on Contact us. 9. Click on twitter icon with a logged account |  |  | Passed
56 |  |  |  | Verifying if the "Contact us" link work properly | link Should redirect user to correct page | Found as per expectation | None | 1. Open Browser https://www.bdstall.com/ 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Contact us 7. Goto the URL https://ssrd.io 8. Click on Contact us. 9. Click on twitter icon with a logged account |  |  | Passed
57 |  |  |  | Verifying that the "Contact Us" functionality works across different devices (desktop, mobile) when using Facebook, Twitter, or LinkedIn | Should work seamlessly across various devices | Found as per expectation | Desktop,Mobile | 1. Open Browser https://www.bdstall.com/ 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Contact us 7. Goto the URL https://ssrd.io 8. Click on Contact us. 9. Click on twitter icon with a logged account |  |  | Passed
58 | Password Reset |  | Forget password | Verifying that forget password link should be present on the login screen | Forgot Password" link should be visible and clickable on the login screen. | Found as per expectation | None | 1. Open Browser https://www.bdstall.com/ 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Contact us 7. Goto the URL https://ssrd.io 8. Click on Contact us. 9. Click on twitter icon with a logged account 2. Click on Login button in the right corner. |  |  | Passed
59 |  |  |  | Verifying that on clicking on the forget password link forget password page should open. | Clicking "Forgot Password" should open the password recovery page. | Found as per expectation | None | 1. Open Browser https://www.bdstall.com/ 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Contact us 7. Goto the URL https://ssrd.io 8. Click on Contact us. 9. Click on twitter icon with a logged account 2. Click on Login button in the right corner. |  |  | Passed
60 |  |  |  | Verifying that the email field is present on the forget password page to recover the password. | Email field should be present on the "Forgot Password" page. | Found as per expectation | None | 1. Open Browser https://www.bdstall.com/ 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Contact us 7. Goto the URL https://ssrd.io 8. Click on Contact us. 9. Click on twitter icon with a logged account 2. Click on Login button in the right corner. |  |  | Passed
61 |  |  |  | Verifying as the user update password, the user should log out from all browser and devices. | Updating the password should log the user out from all browsers and devices. | Not found as per expectation | Browsers- Google Chrome, Microsoft Edge | 1. Open Browser https://www.bdstall.com/ 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Contact us 7. Goto the URL https://ssrd.io 8. Click on Contact us. 9. Click on twitter icon with a logged account 2. Click on Login button in the right corner. |  |  | Passed
62 |  |  |  | Verifying Submit button should be present on the page. | Submit button should be present on the page. | Found as per expectation | None | 1. Open Browser https://www.bdstall.com/ 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Contact us 7. Goto the URL https://ssrd.io 8. Click on Contact us. 9. Click on twitter icon with a logged account 2. Click on Login button in the right corner. |  |  | Passed
63 |  |  |  | Verifying the whole button should be clickable not only the button text. | The entire button, not just the text, should be clickable. | Found as per expectation | None | 1. Open Browser https://www.bdstall.com/ 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Contact us 7. Goto the URL https://ssrd.io 8. Click on Contact us. 9. Click on twitter icon with a logged account 2. Click on Login button in the right corner. |  |  | Passed
64 |  |  |  | Verifying the displayed error message for unregistered should be meaningful. | Error message for unregistered users should be clear and informative. | Found as per expectation | None | 1. Open Browser https://www.bdstall.com/ 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Contact us 7. Goto the URL https://ssrd.io 8. Click on Contact us. 9. Click on twitter icon with a logged account 2. Click on Login button in the right corner. |  |  | Passed
65 |  |  |  | Verifying the confirmation message check your email to recover the password should be displayed after clicking on the button by entering the registered email id. | A confirmation message should appear to check the email for password recovery. | Found as per expectation | None | 1. Open Browser https://www.bdstall.com/ 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Contact us 7. Goto the URL https://ssrd.io 8. Click on Contact us. 9. Click on twitter icon with a logged account 2. Click on Login button in the right corner. |  |  | Passed
66 |  |  |  | Verifying that the user will get an email after entering a valid email id in forget password. | User should receive an email after entering a valid email ID in "Forgot Password." | Not found as per expectation | None | 1. Open Browser https://www.bdstall.com/ 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Contact us 7. Goto the URL https://ssrd.io 8. Click on Contact us. 9. Click on twitter icon with a logged account 2. Click on Login button in the right corner. |  |  | Passed
67 |  |  |  | Verifying the email which the user gets against forgot password should be displayed in the inbox, not in the spam folder. | The password recovery email should appear in the inbox, not the spam folder. | Not found as per expectation | None | 1. Open Browser https://www.bdstall.com/ 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Contact us 7. Goto the URL https://ssrd.io 8. Click on Contact us. 9. Click on twitter icon with a logged account 2. Click on Login button in the right corner. |  |  | Passed
68 |  |  |  | Verifying the user will get the forget password email from info@sitename.com. | The password recovery email should be sent from info@sitename.com. | Not found as per expectation | None | 1. Open Browser https://www.bdstall.com/ 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Contact us 7. Goto the URL https://ssrd.io 8. Click on Contact us. 9. Click on twitter icon with a logged account 2. Click on Login button in the right corner. |  |  | Passed
69 |  |  |  | Verifying the heading displayed in forget password screen should be ” Forget Password “ | The heading should be "Forgot Password." | Not found as per expectation | None | 1. Open Browser https://www.bdstall.com/ 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Contact us 7. Goto the URL https://ssrd.io 8. Click on Contact us. 9. Click on twitter icon with a logged account 2. Click on Login button in the right corner. |  |  | Passed
70 | File Upload |  | Uploading File | Verifying upload file button or link is present. | "Upload File" button or link should be present. | Found as per expectation | None | 1. Go to the URL http://localhost:1337 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Transactions |  |  | Passed
71 |  |  |  | Verifying the upload button or link should be clickable. | "Upload File" button or link should be clickable. | Found as per expectation | None | 1. Go to the URL http://localhost:1337 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Transactions 7. Click on Update button |  |  | Passed
72 |  |  |  | Verifying that the whole button including the button text should be clickable. | The entire button, including the text, should be clickable. | Found as per expectation | None | 1. Go to the URL http://localhost:1337 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Transactions 7. Click on Upload button anywhere other than text on the button |  |  | Passed
73 |  |  |  | Verifying an error message shown if the file size is large than the allowed one. | An error message should be displayed if the file size exceeds the allowed limit. | Found as per expectation | None | 1. Go to the URL http://localhost:1337 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Transactions 7. Click on choose file 8. Choose file larger that exceeds maximum size of the required file 9. Click on Update |  |  | Passed
74 |  |  |  | Verifying an error message if the file is empty and has no content. | An error message should appear for an empty file. | Found as per expectation | None | 1. Go to the URL http://localhost:1337 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Transactions 7. Click on choose file 8. Choose an empty file 9. Click on Upload |  |  | Passed
75 |  |  |  | Drag and drop functionality should work properly for the allowed file types. | Drag and drop should work correctly for allowed file types. | Found as per expectation | None | 1. Go to the URL http://localhost:1337 2. Click on the Signup button in the right corner. 3. Enter an registered email 4. Enter registered account password 5. Click on login 6. Click on Transactions 7. Drag a file to choose file 8. Click on Update |  |  | Passed
Negative test
mmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmm

## Test Summary Report
Test Case Report | [5 empty] | Result :
Project Name | Bdstall
Module Name | Account,User authentication,User registration |  |  |  |  | Total No. | Status | New Features:- | Testing Scope:-
Feature Name | Register Account ,Account Login, Search Functionality
Test Case Version | 1 |  |  |  |  | 79 | PASS
Written By | Progga Roy |  |  |  |  | 5 | FAIL
Executed By | Progga Roy |  |  |  |  | 0 | Not Executed
Reviewed By | Ehsanul Alam Sabbir |  |  |  |  | 0 | Out of Scope
TEST EXECUTION REPORT
Testing Environment : Google Chrome Browser
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 79 | 5 | 0 | 0 | 84
Grand Total | 79 | 5 | 0 | 0 | 84
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting
#SL 01
Issue: Missing eye-icon on the password field
Reproducing Steps:
1. Open Browser https://www.bdstall.com/
2. Click on the "Login" button in the right corner.
3. Locate the password field
4. Observe that the eye icon is missing
Env:
Module: Login
Priority: P1
Severity: High
Screenshot : Missing Eye-icon.png
Expected: Password field should have an eye icon to allow users to toggle visibility
Responsible QA: Progga Roy
Bug Reporting
#SL 02
Issue: Manual Login not working. Page refreshes without loggin in the homepage/dashboard
Reproducing Steps:
1. Open Browser https://www.bdstall.com/l.com/
2. Click on the "Login" button in the right corner.
3. Enter correct credentials
4.Click on "login" button or press enter
Env:
Module: Login
Priority: P0
Severity: High
Screenshot : Manual Login Failed.png
Expected: Successfully logged in and redirect on the home/dashboard
Responsible QA: Progga Roy
Bug Reporting
#SL 03
Issue: Cursor should be remain after open the login page by defult
Reproducing Steps:
1.Open browser https://www.bdstall.com/
1. Open the login page.
2. Observe whether the cursor is placed automatically in the Username field.
3. If not, click on the Username field.
4. Try refreshing the page and check if the cursor remains in the field.
Env: Login
Module: Registration
Priority: P3
Severity: Minor
Screenshot: Error_Cursor.png
Expected: Verification email should be sent to user's email
Responsible QA: Progga Roy
Bug Reporting
#SL 04
Issue: "No Results Found" Message Not Displayed in Search Functionality
Reproducing Steps:
1. Open browser https://www.bdstall.com
2.Locate the search bar and click on it.
3.Enter an invalid product name, such as "xyz123" or "@#*&^%$".
4.Click on the search button or press Enter.
Env: Search Functionality
Module: Search
Priority: P3
Severity: Minor
Screenshot: Massege_error
Expected: Resend link should be available if user didn't receive email link
Responsible QA: Progga Roy
Bug Reporting
#SL 05
Issue: Search Suggestions Not Displayed for Invalid Search Queries
Reproducing Steps:
1. Open browser https://www.bdstall.com.bd/
2.Locate the search bar and click on it.
3. Start typing an incomplete or incorrect product name, such as "Mob" or "Lapto".
4. Observe whether any suggestions (like "Mobile, Mobile Case, Laptop, Laptop Bag") appear.
Env: Search Functionality
Module: Search
Priority: P3
Severity: Minor
Screenshot:Search error
Expected: Logged out from other browsers and devices after updating password
Responsible QA: Adrita Alam

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (84/84)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/84)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (79/84)*100 = 94.0%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (5/84)*100 = 6.0%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/84)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A